## CIP Tasks 2026
Capital Improvement Plan Development Timeline Incremental Approach - Draft 1
|  | Month 1 | Month 2 |  | Month 3 |  | Month 4
Task | Lead |  | SB Mtg 1 | SB Mtg 2 | SB Mtg 1 | SB Mtg 2 | SB Mtg 1 | SB Mtg 2
Compile existing plans, inventories, equipment lists, assessments | Treasurer/Grant Administrator | X
Selectboard Discussion of Process/Timeline | Selectboard |  | X
Selectboard Review/Discuss Highway Equipment Inventory and EQ Lifecycle | Selectboard + Highway Supervisor |  |  | X
Develop 1st Draft of Highway Equipment Replacement Plan based on Selectboard & Highway Supervisor Input | Treasurer/Grant Administrator |  |  | X | X
Selectboard Review/Revise 1st Draft of Equipment Replacement Plan | Selectboard |  |  |  | X
Selectboard Review/Discuss Building & Facilities Inventory & Upcoming Projects | Selectboard |  |  |  | X
Develop 1st Draft of Capital Improvement Plan for Buildings & Facilities based on Selectboard Input | Treasurer/Grant Administrator |  |  |  | X | X
Review/Revise 1st Draft of Capital Improvement Plan for Buildings & Facilities | Selectboard |  |  |  |  | X
Selectboard Review/Discuss Upcoming Road Projects, including a presentation by the Rutland Regional Planning Commission on the State's Municipal Roads Program's Drainage Infrastructure Resource Tool and other mapping tools and data bases | Selectboard + Highway Supervisor |  |  |  |  | X
Develop 1st Draft of Capital Improvement Plan for Roads based on Selectboard +Highway Supervisor Input | Treasurer/Grant Administrator |  |  |  |  | X | X
Selectboard Review/Revise Captial Improvement Plan for Roads | Selectboard + Highway Supervisor | [5 empty] | X
Incorporate all input from Selectboard into Equipment Replacement & Capital Improvement Plans | Treasurer/Grant Administrator | [5 empty] | X | X
Selectboard Review of Equipment Replacement & Capital Improvement Plans | Selectboard + Highway Supervisor | [6 empty] | X
|  | Sep | Oct | Nov | Dec | Jan
Format and distribute First Draft CIP to boards and public | Treasurer/Grant Administrator | X
Hold public discussion / hearing on draft CIP | Selectboard | X
Revise CIP based on feedback (timing, funding, scope) | Treasurer/Grant Administrator | X
Review capital reserves, debt, and affordability for FY2028 | Selectboard |  | X
Adjust phasing/scopes; prepare near‑final CIP draft | Treasurer/Grant Administrator |  | X
Selectboard review and final edits | Selectboard |  | X
Integrate CIP into proposed FY2028 budget (capital lines, reserve contributions, projects) | Treasurer/Grant Administrator |  |  | X
Draft CIP summary for 2026 Town Report | Treasurer/Grant Administrator |  |  | X
Minor adjustments based on late information (storms, new grants, etc.) | Selectboard |  |  |  | X | X