CIP Development Checklist

April to November 2026

Goal: Adopt a five-year Capital Improvement Plan (CIP) in November 2026 to guide the FY2028 budget and appear in the 2026 Town Report (for Town Meeting 2027).

You can use the □ boxes to track completion.

APRIL 2026 – Kickoff and Scope

Selectboard and Staff

- □ Place “Capital Improvement Plan – Kickoff” on an April Selectboard agenda.

- □ Confirm 5-year window for CIP (e.g., FY2028–FY2032).

- □ Clarify that the CIP is a planning document, not a spending authorization.

- □ Appoint a CIP working team (e.g., 1–2 selectboard members, treasurer/clerk, road foreman, fire rep; optional planning/conservation/building committee reps).

- □ Decide whether to request support from regional planning commission (RPC) or other technical assistance.

- □ Approve a basic work schedule (monthly CIP agenda item April–November).

Deliverables

- □ Written CIP scope and process summary

- □ List of departments and boards expected to submit capital needs

MAY 2026 – Data Gathering and Asset Inventory

Staff / Working Team

- □ Compile existing documents:

  - □ Road & culvert inventories; VTrans bridge ratings

  - □ Lists of town vehicles/equipment with age and condition

  - □ Prior capital plans (if any)

  - □ Any building assessments, energy audits, facility reports

  - □ Known commitments (grants awarded, mandated upgrades, etc.)

- □ Draft and send a “Capital Needs Request” memo to:

  - □ Road Dept

  - □ Fire/Rescue

  - □ Town Office/Clerk/Treasurer

  - □ Library

  - □ Recreation/Conservation

  - □ Any Building/Facilities or Energy Committee

- □ In the memo, request for each item:

  - □ Project/equipment name and brief description

  - □ Rough cost range (e.g., <$50k, $50–200k, >$200k)

  - □ Desired year(s) and urgency

- □ Set a response deadline: end of June 2026.

Deliverables

- □ Draft inventory of major town assets

- □ Capital Needs Request memo with clear deadline

JUNE 2026 – Department Input and Preliminary Project List

Departments / Committees

- □ Submit capital needs to working team by deadline:

  - □ Road Dept: paving, major culverts/bridges, equipment

  - □ Fire/Rescue: apparatus and major gear

  - □ Clerk/Office/Library: building/IT/records projects

  - □ Recreation/Conservation: trails, parks, access, facility needs

Staff / Working Team

- □ Compile responses into a single spreadsheet with columns:

  - □ Project name

  - □ Department/lead

  - □ Description

  - □ Est. cost range

  - □ Preferred year(s)

  - □ Notes (safety, legal, grant potential, etc.)

Selectboard

- □ Review preliminary list at a late-June meeting.

- □ Identify obvious “must-do” vs. “nice-to-have” projects.

Deliverables

- □ Consolidated Preliminary Capital Project List (no schedule yet)

JULY 2026 – Cost Refinement and Prioritization Criteria

Staff / Working Team

- □ Request refined estimates on the most important items (quotes, recent bid comparables, VTrans advice, etc.).

- □ Consult RPC/engineers for big projects (bridges, major culverts, buildings) as needed.

Selectboard

- □ Adopt prioritization criteria (4–6 items), such as:

  - □ Safety / legal compliance

  - □ Risk reduction / climate resilience

  - □ Grant leverage and outside funding

  - □ Cost avoidance (avoiding higher future costs)

  - □ Service impact / community benefit

- □ Direct the working team to assign priority levels (High/Medium/Low).

Staff / Working Team

- □ Add priority levels to the project spreadsheet.

Deliverables

- □ Updated project list with improved cost ranges

- □ Written, approved prioritization criteria

- □ Priority level for each project

AUGUST 2026 – Draft 5-Year Schedule and Funding Concepts

Staff / Working Team

- □ Draft a 5-year schedule (e.g., FY2028–FY2032):

  - □ Place high-priority projects in earlier years where feasible.

  - □ Sequence planning/design before construction.

  - □ Spread out large costs to avoid spikes.

- □ Identify likely funding sources for each project:

  - □ Local: general fund, capital reserves, possible bonds

  - □ Outside: state highway aids, Class 2 paving, structures grants, Better Roads, FEMA, clean water, VHCB, etc.

  - □ Mark projects that depend on grant success.

- □ For each year, estimate:

  - □ Total project costs

  - □ Estimated grant/outside funds

  - □ Local share required

Selectboard

- □ Hold a work session to review:

  - □ Year-by-year schedule

  - □ Annual local share totals

  - □ Obvious affordability issues

Deliverables

- □ First Draft 5-Year CIP Schedule with funding notes and annual totals

SEPTEMBER 2026 – Public Input and Second Draft

Staff / Working Team

- □ Finalize the First Draft CIP in a readable format (narrative + table).

- □ Distribute draft to:

  - □ Road Dept, Fire/Rescue, Library, Rec, Planning, Conservation

  - □ Post online and provide copies at Town Office

Selectboard

- □ Schedule a public discussion (at a regular meeting or special session).

- □ Present:

  - □ Summary of major projects and timing

  - □ Estimated role of grants vs. local dollars

  - □ How the CIP helps avoid surprises

- □ Take resident and department feedback.

Staff / Working Team

- □ Adjust:

  - □ Project timing (phasing, deferrals)

  - □ Funding assumptions (where unrealistic)

  - □ Add/remove/refine projects as warranted

Deliverables

- □ Second Draft CIP reflecting public and internal feedback

- □ Brief summary of key comments and changes

OCTOBER 2026 – Budget Alignment and Final Revisions

Staff / Treasurer / Clerk

- □ Review capital reserve balances and projections.

- □ Review any outstanding debt and annual payments.

- □ Estimate what annual capital/reserve contributions are affordable for FY2028.

Working Team

- □ “Stress-test” each CIP year:

  - □ Confirm the local share is realistic.

  - □ Adjust phasing or scopes where years are too heavy.

  - □ Flag “only if grant is awarded” projects.

- □ Prepare a near-final CIP draft with:

  - □ Clear descriptions and cost ranges

  - □ Funding sources and assumptions

  - □ Rationale for timing and priorities

Selectboard

- □ Review near-final draft; suggest last edits.

Deliverables

- □ Near-final CIP draft aligned with FY2028 budget assumptions

- □ Internal note on key financial assumptions and risks

NOVEMBER 2026 – Adoption and Integration

Selectboard

- □ Place CIP adoption on early-/mid-November agenda.

- □ Make any final minor changes.

- □ Adopt the CIP by motion, clearly stating:

  - □ It is a planning tool, not an appropriation

  - □ It will be updated annually

Staff / Treasurer / Clerk

- □ Use the adopted CIP to:

  - □ Inform capital reserve contributions for the proposed FY2028 budget.

  - □ Decide which projects are formally proposed in FY2028.

  - □ Identify 2027 grant applications needed to implement the CIP.

- □ Prepare a CIP Summary (1–2 pages) for the 2026 Town Report (for Town Meeting 2027).

Deliverables

- □ Adopted 5-Year CIP (e.g., FY2028–FY2032)

- □ CIP summary text and charts/tables for Town Report

- □ Linkage between CIP and proposed FY2028 budget

DECEMBER 2026 – Brief Follow-Through

- □ Make any minor adjustments based on late-year information (e.g., storms, new grants).

- □ Confirm what from Year 1 of the CIP is actually in the proposed FY2028 budget.

- □ Plan to update the CIP each fall going forward.