## CIP Process
Capital Improvement Plan Development Process
Timeline Template
High‑Level Phases
Phase | Lead | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Project kickoff & scope | SB / Staff | X
Data gathering & asset inventory | Staff |  | X | X
Department capital needs submissions | All depts |  |  | X
Cost refinement & prioritization criteria | SB / Staff |  |  |  | X
Draft 5‑year schedule & funding concepts | Staff |  |  |  |  | X
Public review & second draft | SB / Staff | [5 empty] | X
Budget alignment & final revisions | Staff / SB | [6 empty] | X
Formal adoption & integration w/ budget | SB / Treasurer | [7 empty] | X
Minor year‑end adjustments | Staff | [8 empty] | X
Detailed Task Timeline
Task | Lead | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Approve CIP scope, 5‑year window, and process | SB | X
Appoint CIP working team & confirm meeting schedule | SB | X
Compile existing plans, inventories, equipment lists, assessments | WT/Staff |  | X | X
Send “Capital Needs Request” memo to all departments/committees | WT/Staff |  | X
Departments identify projects, costs (rough), and preferred timing | Depts |  |  | X
Consolidate all submissions into preliminary project list | WT/Staff |  |  | X
SB review of preliminary list and identification of “must‑do” items | SB |  |  | X
Refine cost estimates for higher‑priority items | WT/Depts |  |  |  | X
Adopt formal prioritization criteria | SB |  |  |  | X
Apply priority levels (High/Med/Low) to each project | WT/Staff |  |  |  | X
Build draft 5‑year project schedule (by year) | WT/Staff |  |  |  |  | X
Identify likely funding sources and estimate annual local shares | WT/Staff |  |  |  |  | X
SB work session to review first draft schedule and annual totals | SB |  |  |  |  | X
Format and distribute First Draft CIP to boards and public | WT/Staff | [5 empty] | X
Hold public discussion / hearing on draft CIP | SB | [5 empty] | X
Revise CIP based on feedback (timing, funding, scope) | WT/Staff | [5 empty] | X
Review capital reserves, debt, and affordability for FY2028 | TR/Staff | [6 empty] | X
Adjust phasing/scopes; prepare near‑final CIP draft | WT/Staff | [6 empty] | X
SB review and final edits | SB | [6 empty] | X
Formal Selectboard adoption of CIP | SB | [7 empty] | X
Integrate CIP into proposed FY2028 budget (capital lines, reserve contributions, projects) | TR/SB | [7 empty] | X
Draft CIP summary for 2026 Town Report | WT/Staff | [7 empty] | X
Minor adjustments based on late information (storms, new grants, etc.) | WT/Staff | [8 empty] | X
SB = Selectboard
TR = Treasurer
WT = Work Team (if using)