## How to Use
CHIP Risk Matrix
About The Matrix
Every CHIP project has risks, but the risks will not be the same for every project or community. This matrix identifies common risks that municipalities may want to consider when evaluating and carrying out a CHIP public-private partnership.
Use the matrix as a starting point for discussion, not a checklist of risks that will apply to every project. Review the risks with your municipal project team and development partner. Consider which risks apply to your project, how they could affect other parts of the project, and whether additional review is needed.
The matrix provides a general assessment of each risk and common ways it may be reduced. It also identifies who is typically best positioned to manage the risk. These are general examples. Each municipality should make its own assessment based on the project, the partners, community priorities, and the municipality's financial capacity and comfort with risk.
How to Use It
1. Review each risk and decide whether it applies to your project.
2. Consider how likely each risk is and how serious its effects could be. Adjust the impact if local conditions make the risk more or less serious.
3. Look at how one risk could affect other parts of the project.
4. Discuss steps that could reduce or manage the risk.
5. Discuss which partner is best positioned to manage the risk. “Usually Managed By” is a starting point, not a rule.
6. Seek legal, financial, engineering, or other professional advice when needed.
7. Select mitigation steps and assign a person to monitor the risk.
8. Revisit the risks when financing, permits, design, costs, schedules, or project responsibilities change.
Important Note
Risks can interact. A permitting delay can affect financing; a site problem can affect cost and schedule. Consider both the direct effect of a risk and what it could change elsewhere in the project.
Rating Key
High - could prevent the project from moving forward, create a major funding gap, cause a major delay, or place public resources at significant risk.
Medium - could increase costs, cause delays, require project changes, or demand added management attention.
Low - likely to have a limited or indirect effect and may be manageable through routine oversight.
Risk Allocation
Public - usually managed mainly by the municipality.
Private - usually managed mainly by the developer.
Shared - requires coordination by both partners.

## Risk Matrix
Topic | Risk | Why It Matters | Overall Impact | Most Affected Project Type | Common Ways to Reduce the Risk | Usually Managed By | Impact to Municipality | Impact to Developer
Project Selection & Early Planning | Community need is not clearly understood | The project may not address the housing or infrastructure problem the community most needs to solve. | High | Housing | Use housing needs data, market information, plans, and public input to define the need before choosing a solution. | Public | High | Medium
Project Selection & Early Planning | Project does not align with community goals | A project that conflicts with adopted plans or local priorities may lose support or require major changes. | High | Both | Compare the proposal with municipal plans, zoning, housing goals, capital plans, and public priorities. | Public | High | Medium
Project Selection & Early Planning | Public benefit is unclear or overstated | The municipality may take on obligations without receiving enough housing, infrastructure, or community benefit. | High | Both | Define expected public benefits in measurable terms and revisit them as the project changes. | Public | High | Medium
Project Selection & Early Planning | Developer lacks needed experience or capacity | The development team may struggle to complete complex financing, permitting, construction, or reporting tasks. | High | Both | Review experience, references, completed projects, staffing, financial capacity, and the strength of the full development team. | Shared | High | High
Project Selection & Early Planning | Site control is uncertain | The project may spend time and money on a site the developer or municipality cannot ultimately use. | High | Both | Confirm ownership, purchase agreements, options, easements, and other rights needed to carry out the project. | Shared | High | High
Municipal Readiness & Governance | Municipality lacks a clear project lead | Tasks may be missed, information may be inconsistent, and decisions may be delayed. | High | Both | Name a municipal lead and define who coordinates staff, consultants, the legislative body, and the developer. | Public | High | Medium
Municipal Readiness & Governance | Municipal roles and decision authority are unclear | Staff, boards, and consultants may give conflicting direction or make decisions without proper authority. | High | Both | Document roles, approval steps, decision authority, and when issues must return to the legislative body. | Public | High | Medium
Municipal Readiness & Governance | Municipality lacks needed professional expertise | The municipality may not recognize important legal, financial, engineering, valuation, or development issues. | High | Both | Identify expertise gaps early and retain independent legal, financial, engineering, appraisal, or development advisors as needed. | Public | High | Medium
Municipal Readiness & Governance | Leadership or staff turnover disrupts the project | Knowledge may be lost and prior decisions may be misunderstood during a project that lasts several years. | Medium | Both | Keep complete records, use shared project files, document decisions, and plan for handoffs. | Public | Medium | Medium
Financial & Market | Construction costs increase | Higher labor, material, or contractor costs can create a funding gap or force design changes. | High | Both | Use current estimates, contingencies, value engineering, bid validation, and clear responsibility for cost overruns. | Private | Medium | High
Financial & Market | Interest rates or financing costs increase | Higher borrowing costs can make the project or CHIP financing less affordable. | High | Both | Stress-test rates, seek financing early, consider fixed rates when appropriate, and update the financing model regularly. | Shared | Medium | High
Financial & Market | Developer financing is delayed or unavailable | The housing project may stall even if public approvals and infrastructure plans are ready. | High | Housing | Set financing milestones, confirm lender or investor interest, and avoid major public commitments before key private financing is reasonably secure. | Private | Medium | High
Financial & Market | Tax increment is lower or later than projected | Less or delayed increment may reduce funds available to repay eligible infrastructure costs or debt. | High | Both | Use conservative assessed-value and timing assumptions, sensitivity testing, independent review, and clear shortfall provisions. | Shared | High | High
Financial & Market | Housing demand, rents, or sales are weaker than expected | Units may lease or sell more slowly, reducing project cash flow and delaying assessed value. | High | Housing | Use market analysis, realistic pricing and absorption assumptions, phased development, and sensitivity testing. | Private | Medium | High
Financial & Market | Project cash flow does not match reimbursement or debt timing | A party may need to carry costs longer than expected or may not have cash available when bills come due. | High | Both | Build a month-by-month cash-flow plan, define reimbursement timing, identify interim financing, and maintain reserves or contingencies. | Shared | High | High
Site, Design & Construction | Environmental contamination is discovered | Cleanup can add major cost, delay, liability, and permitting requirements. | High | Both | Complete environmental review early, define cleanup responsibilities, seek available brownfield resources, and include contingencies. | Shared | High | High
Site, Design & Construction | Unforeseen soil, ledge, groundwater, or site conditions arise | Unknown conditions can change foundations, utilities, roads, schedules, and budgets. | High | Infrastructure | Use surveys, geotechnical work, test pits, utility investigation, contingencies, and change procedures. | Shared | High | High
Site, Design & Construction | Design errors or incomplete plans cause changes | Errors can lead to change orders, rework, delays, and disputes over responsibility. | High | Both | Use qualified designers, quality-control reviews, constructability review, and clear professional responsibility. | Private | Medium | High
Site, Design & Construction | Utility conflicts or capacity limits emerge | Existing water, wastewater, stormwater, power, or communications systems may not support the planned work. | High | Infrastructure | Confirm utility locations and capacity early, coordinate with providers, and identify upgrade responsibilities before final design. | Shared | High | High
Site, Design & Construction | Contractor performance problems occur | Poor performance can affect cost, quality, safety, and schedule. | High | Both | Use qualification checks, references, bonding or other assurances, clear contracts, and active construction oversight. | Private | Medium | High
Site, Design & Construction | Construction is delayed | Delays can increase financing costs, threaten permits, postpone housing delivery, and reduce or delay tax increment. | High | Both | Use realistic schedules, track critical milestones, identify delay responsibilities, and create contingency plans. | Private | High | High
Legal, Regulatory & Compliance | Permits or approvals are delayed, appealed, or expire | The project may lose time, financing, or design flexibility and may need to restart parts of the approval process. | High | Both | Map approvals early, assign responsibility, build realistic timelines, monitor expiration dates, and maintain complete records. | Shared | High | High
Legal, Regulatory & Compliance | Property rights, easements, or access are incomplete | Infrastructure or construction may be blocked if the required property interests are not in place. | High | Infrastructure | Complete title, survey, easement, access, and ownership review before construction commitments. | Shared | High | High
Legal, Regulatory & Compliance | CHIP requirements are not met | The project may lose eligibility, reimbursement, or approval, and the municipality may face compliance problems. | High | Both | Assign compliance responsibility, use a requirements calendar, keep records, and obtain legal or program guidance when needed. | Public | High | Medium
Legal, Regulatory & Compliance | Procurement or contracting requirements are not followed | Costs may become ineligible or contracts may be challenged. | High | Infrastructure | Identify which procurement rules apply, follow written procedures, document competition and decisions, and obtain legal review when needed. | Public | High | Low
Partnership, Communication & Community | Roles and responsibilities between partners are unclear | Tasks may be duplicated or missed, and disputes may arise when conditions change. | High | Both | Use pre-development, development, and CHIP agreements; responsibility charts; milestones; and regular project check-ins. | Shared | High | High
Partnership, Communication & Community | Important information is not shared early | Partners may make decisions using different facts or learn about problems too late to respond well. | High | Both | Set regular meetings and reporting expectations, share good and bad news promptly, and identify who must receive key information. | Shared | High | High
Partnership, Communication & Community | Trust or working relationships break down | Even manageable issues can become disputes if the parties no longer believe they can solve problems together. | High | Both | Build relationships before problems arise, follow through on commitments, document decisions, and use agreed dispute-resolution steps. | Shared | High | High
Partnership, Communication & Community | Community or political support declines | Opposition can delay approvals, change municipal priorities, or reduce willingness to continue public investment. | High | Both | Engage early, explain benefits and risks clearly, provide consistent information, respond to concerns, and avoid promises outside municipal control. | Public | High | Medium
Long-Term Performance | Infrastructure ownership, acceptance, or maintenance obligations are unclear | The municipality may inherit unexpected costs or accept infrastructure that is incomplete or does not meet standards. | High | Infrastructure | Define ownership, inspection, acceptance, warranties, maintenance standards, funding, and handoff requirements in writing. | Shared | High | Medium